## Master BoM
GND OPTUS FIBRE — MASTER CONSOLIDATED BILL OF MATERIALS
Jobs: EO35714250, EO36932149, EO38407216, EO46092659, EO49466087 ¦ Updated: 10 Mar 2026 ¦ 🔴 GAP = not in Optus template — must be resolved before pricing
ID | SECTION | ITEM DESCRIPTION | DISCIPLINE | UOM | IN TEMPLATE? | EO35714250 | EO36932149 | EO38407216 | EO46092659 | EO49466087 | GAP FLAG | GAP / ACTION REQUIRED
▶ STANDARD ITEMS
S01 | STANDARD | Site Establishment | Preliminaries & Site | Each (Ea) | YES | — | — | — | — | —
S02 | STANDARD | Boundary Surveying | Preliminaries & Site | Each (Ea) | YES | — | — | — | — | —
S03 | STANDARD | Traffic & Pedestrian Management | Preliminaries & Site | Each (Ea) | YES | — | — | — | — | —
S04 | STANDARD | 50mm Duct Installation | Civil & Pits | Metre | YES | 488.06 | 352.38 | 14.5 | 22 | 221.5
S05 | STANDARD | 1 x 32mm (within Existing Carrier/Private Network) | Civil & Pits | Metre | YES | — | — | — | — | —
S06 | STANDARD | Telstra-Optus Breakout - Core Drill & Jackmoon Seal | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
S07 | STANDARD | Telstra-Optus Breakout - P100 with 4xP32 Subduct | Civil & Pits | Metre | YES | — | — | — | — | —
S08 | STANDARD | P4 Pit (Optus Approved) – S&I | Civil & Pits | Each (Ea) | YES | 3 | 4 | — | — | 3
S09 | STANDARD | P4 Pit (Optus Approved) – Over Existing Network S&I | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
S10 | STANDARD | P5 Pit (Optus Approved) – S&I | Civil & Pits | Each (Ea) | YES | 1 | — | — | 1 | —
S11 | STANDARD | P5 Pit (Optus Approved) – Over Existing Network S&I | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
S12 | STANDARD | A8 Pit (Optus Approved) – S&I | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
S13 | STANDARD | A8 Pit (Optus Approved) – Over Existing Network S&I | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
S14 | STANDARD | P9 Pit & Concrete Infill Lid S&I - VIC only | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
S15 | STANDARD | P9 Pit & Concrete Infill Lid (over Existing Network) S&I - VIC Only | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
S16 | STANDARD | A10 Pit (Optus Approved) – S&I | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
S17 | STANDARD | A10 Pit (Optus Approved) – Over Existing Network S&I | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
S18 | STANDARD | 36 SMOF External Hauling | Cable Hauling & Aerial | Metre | YES | 612.77 | — | — | 561.88 | 225.5
S19 | STANDARD | 72 SMOF External Hauling | Cable Hauling & Aerial | Metre | YES | — | — | — | — | 2995.34
S20 | STANDARD | 96 SMOF External Hauling | Cable Hauling & Aerial | Metre | YES | — | — | — | — | —
S21 | STANDARD | 144 SMOF External Hauling | Cable Hauling & Aerial | Metre | YES | — | 1394.46 | 1543.19 | — | —
S22 | STANDARD | 312 SMOF External Hauling | Cable Hauling & Aerial | Metre | YES | — | — | — | — | —
S23 | STANDARD | 72 SMOF Overblowing | Cable Hauling & Aerial | Metre | YES | — | — | — | — | —
S24 | STANDARD | 96 SMOF Ploughing | Cable Hauling & Aerial | Metre | YES | — | — | — | — | —
S25 | STANDARD | Rural Marker Posts - Stamped Install Only | Preliminaries & Site | Each (Ea) | YES | — | — | — | — | —
S26 | STANDARD | Urban Marker Posts - Install Only | Preliminaries & Site | Each (Ea) | YES | — | — | — | — | —
S27 | STANDARD | Restoration | Preliminaries & Site | Each (Ea) | YES | — | — | — | — | —
S28 | STANDARD | AJL/BJL (312-144) Fully Spliced | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S29 | STANDARD | AJL/BJL (144-72) Fully Spliced | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S30 | STANDARD | AJL/BJL (96-36) Fully Spliced | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S31 | STANDARD | AJL/BJL (72-36) Fully Spliced | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S32 | STANDARD | BJL - 312F | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S33 | STANDARD | BJL - 144F | Splicing & Testing | Each (Ea) | YES | — | 3 | 4 | — | —
S34 | STANDARD | BJL - 96F | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S35 | STANDARD | BJL - 72F | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S36 | STANDARD | AJL - 96F | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S37 | STANDARD | AJL - 72F | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S38 | STANDARD | AJL - 36F | Splicing & Testing | Each (Ea) | YES | 2 | — | — | 1 | 5
S39 | STANDARD | 50mm Penetration | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
S40 | STANDARD | Conduit (Galvanised) | Internal Works | Metre | YES | — | — | — | — | —
S41 | STANDARD | Conduit (Steel Flex) | Internal Works | Metre | YES | — | — | — | — | —
S42 | STANDARD | Conduit (PVC Rigid) | Internal Works | Metre | YES | — | — | — | — | —
S43 | STANDARD | Conduit (PVC Flex) | Internal Works | Metre | YES | — | — | — | — | —
S44 | STANDARD | Conduit (Riser) | Internal Works | Metre | YES | — | — | — | — | —
S45 | STANDARD | Cable Tray (100mm) | Internal Works | Metre | YES | — | — | — | — | —
S46 | STANDARD | Cable Tray (150mm) | Internal Works | Metre | YES | — | — | — | — | —
S47 | STANDARD | Cable Tray (300mm) | Internal Works | Metre | YES | — | — | — | — | —
S48 | STANDARD | 12 SMOF Internal Hauling | Internal Works | Metre | YES | — | — | — | — | —
S49 | STANDARD | 24 SMOF Internal Hauling | Internal Works | Metre | YES | — | — | — | — | —
S50 | STANDARD | 36 SMOF Internal Hauling | Internal Works | Metre | YES | — | — | — | — | —
S51 | STANDARD | 72 SMOF Internal Hauling | Internal Works | Metre | YES | — | — | — | — | —
S52 | STANDARD | Install Cabinet (Wall Mounted) | Internal Works | Each (Ea) | YES | — | — | — | — | —
S53 | STANDARD | Install LGX (Rack Mounted) | Internal Works | Each (Ea) | YES | — | — | — | — | —
S54 | STANDARD | Install Rack | Internal Works | Each (Ea) | YES | — | — | — | — | —
S55 | STANDARD | 12 Way Termination | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S56 | STANDARD | 24 Way Termination | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S57 | STANDARD | 36 Way Termination | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S58 | STANDARD | 72 Way Termination | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S59 | STANDARD | 144 Way Termination | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S60 | STANDARD | 312 Way Termination | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
S61 | STANDARD | Testing of Cable (All Spliced Fibres - Bi-directional at 1310nm & 1550nm) | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
▶ NON-STANDARD ITEMS
N01 | NON-STANDARD | De-Watering of Manholes | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N02 | NON-STANDARD | 100mm Duct Installation | Civil & Pits | Metre | YES | — | — | — | — | —
N03 | NON-STANDARD | A8 Pit & Sika Lid S&I | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N04 | NON-STANDARD | A10 Pit & Sika Lid S&I | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N05 | NON-STANDARD | P5 Pit (Lockable Concrete/Paver Infill Lid) S&I | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N06 | NON-STANDARD | P5 Pit (Lockable Concrete/Paver Infill Lid) over Existing Network S&I | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N07 | NON-STANDARD | P8 Pit (over Existing Network) S&I | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N08 | NON-STANDARD | Dig Down (over Existing Optus IOF Network) | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N09 | NON-STANDARD | Insitu Pit S&I (with Sika lid) | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N10 | NON-STANDARD | Upgrade P5 Pit to A8 Pit - Install Only | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N11 | NON-STANDARD | Upgrade P5 Pit to A10 Pit - Install Only | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N12 | NON-STANDARD | Upgrade P8 Pit to A10 Pit - Install Only | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N13 | NON-STANDARD | Sika Lid & Surround - Install Only | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N14 | NON-STANDARD | Raise Buried P8 Pit - Replace with A8 Pit - Install Only | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N15 | NON-STANDARD | Raise Buried P8 Pit - Replace with A10 Pit - Install Only | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N16 | NON-STANDARD | Testing of Cable (Pre-Installation) | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
N17 | NON-STANDARD | Installation of Strand (Aerial) | Cable Hauling & Aerial | Metre | YES | — | — | — | — | —
N18 | NON-STANDARD | Installation of Fibre Cable (Aerial Existing Strand) | Cable Hauling & Aerial | Metre | YES | — | — | — | — | —
N19 | NON-STANDARD | Delash Existing Cable / Install New Cable (Aerial Existing Strand) | Cable Hauling & Aerial | Metre | YES | — | — | — | — | —
N20 | NON-STANDARD | Recover Existing Cable (Aerial) | Cable Hauling & Aerial | Metre | YES | — | — | — | — | —
N21 | NON-STANDARD | Delash-Re Lash Fibre Loop (Aerial Existing Strand) | Cable Hauling & Aerial | Metre | YES | — | — | — | — | —
N22 | NON-STANDARD | Relocate Aerial Splice to Underground | Splicing & Testing | Each (Ea) | YES | — | — | — | — | —
N23 | NON-STANDARD | Aerial to Underground Pole Assemblies | Civil & Pits | Each (Ea) | YES | — | — | — | — | —
N24 | NON-STANDARD | Pole Testing - Level 1 and 1.5 Tests | Pole Works | Each (Ea) | YES | — | — | — | — | —
N25 | NON-STANDARD | Installation of Alley Arms on Transformers | Pole Works | Each (Ea) | YES | — | — | — | — | —
N26 | NON-STANDARD | Tree Guards | Pole Works | Metre | YES | — | — | — | — | —
N27 | NON-STANDARD | Pole Guards | Pole Works | Each (Ea) | YES | — | — | — | — | —
🔴 GAP ITEMS — NOT IN OPTUS BID TEMPLATE
G01 | GAP | P8 Pit (Standard S&I) | Civil & Pits | Each (Ea) | — | 2 | 3 | 4 | 1 | 5 | 🔴 GAP | SEEN IN: EO35714250 (×2), EO36932149 (×3), EO38407216 (×4), EO46092659 (×1), EO49466087 (×5). ALL 5 JOBS. Template has A8 variants (S12/S13) and P8-over-existing (N07). New P8 S&I is missing. RESOLVE IMMEDIATELY — add to RC1.
G02 | GAP | Conduit Seals | Civil & Pits | Each (Ea) | — | 4 | 10 | 6 | 4 | 10 | 🔴 GAP | SEEN IN: ALL 5 JOBS — EO35714250 (×4), EO36932149 (×10), EO38407216 (×6), EO46092659 (×4), EO49466087 (×10). Every single job. Add to RC2 as standard consumable immediately.
G03 | GAP | 12 SMOF External Hauling | Cable Hauling & Aerial | Metre | — | 247.26 | — | — | — | — | 🔴 GAP | SEEN IN: EO35714250 (247.26m) only. 12F Internal exists (S48). 12F External missing. Add to RC1.
G04 | GAP | FIST BC6 Splice Enclosure (AJL) — RC1 mapping required | Splicing & Testing | Each (Ea) | — | 2 | — | — | 1 | 5 | 🔴 GAP | SEEN IN: EO35714250 (×2), EO46092659 (×1), EO49466087 (×5). 3 jobs, 8 total units. BC6 = enclosure; AJL = splice type. Map BC6 → AJL-36F or AJL-72F depending on fibre count. Confirm with Karen — escalated from MEDIUM to HIGH (3 jobs).
G05 | GAP | YOFC AJL Mini Splice Enclosure — RC1 mapping required | Splicing & Testing | Each (Ea) | — | 1 | — | — | 1 | — | 🔴 GAP | SEEN IN: EO35714250 (×1), EO46092659 (×1). 2 jobs. Map to AJL fibre-count line or add as separate RC1 item. Karen to confirm.
G06 | GAP | Telstra P50 Breakout (direct method) | Civil & Pits | Each (Ea) | — | 2 | 5 | 3 | 2 | 5 | 🔴 GAP | SEEN IN: ALL 5 JOBS — EO35714250 (×2), EO36932149 (×5), EO38407216 (×3), EO46092659 (×2), EO49466087 (×5). 17 total units across 5 jobs. Template has S06/S07 but neither directly maps. MOST URGENT GAP after G01/G02. Confirm method with Optus PE and lock to RC1 line.
G07 | GAP | FIST BE6 Splice Enclosure (BJL) — RC1 mapping required | Splicing & Testing | Each (Ea) | — | — | 3 | 4 | — | — | 🔴 GAP | SEEN IN: EO36932149 (×3), EO38407216 (×4). 2 SA jobs. BE6 = backbone enclosure → map to BJL-144F.
G08 | GAP | Upgrade Telstra ACM Pit to Plastic Pit (for Optus B/O) | Civil & Pits | Each (Ea) | — | — | 2 | — | — | — | 🔴 GAP | SEEN IN: EO36932149 (×2). ACM = asbestos cement — hazmat. Specialist removal required. CHECK DAMIAN before pricing.
G09 | GAP | EM30 — Heritage Item Approval & Compliance (Built Heritage) | Preliminaries & Site | Job | — | — | — | 1 | — | — | 🔴 GAP | SEEN IN: EO38407216 (all 9 sections). Built heritage overlay, North Adelaide SA. Add as Preliminaries item.
G10 | GAP | BEP — Building Entry Point Installation (Mobile Site) | Internal Works | Each (Ea) | — | — | — | — | 1 | 1 | 🔴 GAP | SEEN IN: EO46092659 (×1), EO49466087 (×1). 2 jobs. Every GL168 TXM 5G GF mobile site lead-in likely to have BEP. Add to RC1 as standard mobile site internal item.
G11 | GAP | EM21 — Aboriginal Heritage (Sensitive Area) — CHMP / RAP Engagement | Preliminaries & Site | Job | — | — | — | — | 1 | — | 🔴 GAP | SEEN IN: EO46092659 (both sections). VIC Mornington Peninsula. Drawing explicitly states 'Proposed works are in an Aboriginal Heritage area.' CHMP under Aboriginal Heritage Act 2006 (VIC) may take 6-12 months. HARD STOP — do not mobilise without written approval.
G12 | GAP | NBN Co Pit / Duct Interface — access and RRP-equivalent process unknown | Civil & Pits | Each (Ea) | — | — | — | — | — | 1 | 🔴 GAP | SEEN IN: EO49466087 (Section 009 + NBN bare fibre in multiple Telstra manholes). NBN Co infrastructure in duct path at Thurgoona NSW. Drawing notes 'NBN pit' — NBN-owned manhole. Interface process is DIFFERENT from Telstra RRP. NBN Co requires own field service order via NBN Co Access Seeker/Wholesale process. No RC1 line exists. Damian to confirm NBN access process with Optus before quoting Section 009 scope. Flag for all NSW jobs where NBN Co ducts are in path.
G13 | GAP | Essential Energy HV Cable — Third-party spotter/attendance for bore near live HV | Preliminaries & Site | Job | — | — | — | — | — | 1 | 🔴 GAP | SEEN IN: EO49466087 (Section 008, Pickworth St). Drawing note: 'Essential Energy Underground HV Cable.' Road crossing at this section mandates underbore at 1000mm minimum depth. Working within proximity of live HV underground cable requires: (1) Essential Energy DBYD + live locate, (2) possible Essential Energy-approved spotter on site during excavation/bore, (3) Safe Work NSW excavation near services compliance. No template line for third-party energy attendance. Add provisional sum. Damian to confirm Essential Energy requirements for this section before quoting.

## Gap Register
GND OPTUS FIBRE — GAP REGISTER ¦ Items NOT in Optus Bid Template
Karen resolves each gap (add to RC1/RC2) before job is priced. Priority escalates with job frequency.
GAP ID | ITEM | DISCIPLINE | UOM | FIRST SEEN | ALSO IN (confirmed) | PRIORITY | ACTION REQUIRED
G01 | P8 Pit (Standard S&I) | Civil & Pits | Each (Ea) | EO35714250 | EO36932149, EO38407216, EO46092659, EO49466087 | 🔴 CRITICAL | SEEN IN: EO35714250 (×2), EO36932149 (×3), EO38407216 (×4), EO46092659 (×1), EO49466087 (×5). ALL 5 JOBS. Template has A8 variants (S12/S13) and P8-over-existing (N07). New P8 S&I is missing. RESOLVE IMMEDIATELY — add to RC1.
G02 | Conduit Seals | Civil & Pits | Each (Ea) | EO35714250 | EO36932149, EO38407216, EO46092659, EO49466087 | 🔴 CRITICAL | SEEN IN: ALL 5 JOBS — EO35714250 (×4), EO36932149 (×10), EO38407216 (×6), EO46092659 (×4), EO49466087 (×10). Every single job. Add to RC2 as standard consumable immediately.
G03 | 12 SMOF External Hauling | Cable Hauling & Aerial | Metre | EO35714250 | — | 🟡 MEDIUM | SEEN IN: EO35714250 (247.26m) only. 12F Internal exists (S48). 12F External missing. Add to RC1.
G04 | FIST BC6 Splice Enclosure (AJL) — RC1 mapping required | Splicing & Testing | Each (Ea) | EO35714250 | EO46092659, EO49466087 | 🟠 HIGH | SEEN IN: EO35714250 (×2), EO46092659 (×1), EO49466087 (×5). 3 jobs, 8 total units. BC6 = enclosure; AJL = splice type. Map BC6 → AJL-36F or AJL-72F depending on fibre count. Confirm with Karen — escalated from MEDIUM to HIGH (3 jobs).
G05 | YOFC AJL Mini Splice Enclosure — RC1 mapping required | Splicing & Testing | Each (Ea) | EO35714250 | EO46092659 | 🟠 HIGH | SEEN IN: EO35714250 (×1), EO46092659 (×1). 2 jobs. Map to AJL fibre-count line or add as separate RC1 item. Karen to confirm.
G06 | Telstra P50 Breakout (direct method) | Civil & Pits | Each (Ea) | EO35714250 | EO36932149, EO38407216, EO46092659, EO49466087 | 🔴 CRITICAL | SEEN IN: ALL 5 JOBS — EO35714250 (×2), EO36932149 (×5), EO38407216 (×3), EO46092659 (×2), EO49466087 (×5). 17 total units across 5 jobs. Template has S06/S07 but neither directly maps. MOST URGENT GAP after G01/G02. Confirm method with Optus PE and lock to RC1 line.
G07 | FIST BE6 Splice Enclosure (BJL) — RC1 mapping required | Splicing & Testing | Each (Ea) | EO36932149 | EO38407216 | 🟠 HIGH | SEEN IN: EO36932149 (×3), EO38407216 (×4). 2 SA jobs. BE6 = backbone enclosure → map to BJL-144F.
G08 | Upgrade Telstra ACM Pit to Plastic Pit (for Optus B/O) | Civil & Pits | Each (Ea) | EO36932149 | — | 🔴 CRITICAL | SEEN IN: EO36932149 (×2). ACM = asbestos cement — hazmat. Specialist removal required. CHECK DAMIAN before pricing.
G09 | EM30 — Heritage Item Approval & Compliance (Built Heritage) | Preliminaries & Site | Job | EO38407216 | — | 🔴 CRITICAL | SEEN IN: EO38407216 (all 9 sections). Built heritage overlay, North Adelaide SA. Add as Preliminaries item.
G10 | BEP — Building Entry Point Installation (Mobile Site) | Internal Works | Each (Ea) | EO46092659 | EO49466087 | 🟠 HIGH | SEEN IN: EO46092659 (×1), EO49466087 (×1). 2 jobs. Every GL168 TXM 5G GF mobile site lead-in likely to have BEP. Add to RC1 as standard mobile site internal item.
G11 | EM21 — Aboriginal Heritage (Sensitive Area) — CHMP / RAP Engagement | Preliminaries & Site | Job | EO46092659 | — | 🔴 CRITICAL | SEEN IN: EO46092659 (both sections). VIC Mornington Peninsula. Drawing explicitly states 'Proposed works are in an Aboriginal Heritage area.' CHMP under Aboriginal Heritage Act 2006 (VIC) may take 6-12 months. HARD STOP — do not mobilise without written approval.
G12 | NBN Co Pit / Duct Interface — access and RRP-equivalent process unknown | Civil & Pits | Each (Ea) | EO49466087 | — | 🔴 CRITICAL | SEEN IN: EO49466087 (Section 009 + NBN bare fibre in multiple Telstra manholes). NBN Co infrastructure in duct path at Thurgoona NSW. Drawing notes 'NBN pit' — NBN-owned manhole. Interface process is DIFFERENT from Telstra RRP. NBN Co requires own field service order via NBN Co Access Seeker/Wholesale process. No RC1 line exists. Damian to confirm NBN access process with Optus before quoting Section 009 scope. Flag for all NSW jobs where NBN Co ducts are in path.
G13 | Essential Energy HV Cable — Third-party spotter/attendance for bore near live HV | Preliminaries & Site | Job | EO49466087 | — | 🔴 CRITICAL | SEEN IN: EO49466087 (Section 008, Pickworth St). Drawing note: 'Essential Energy Underground HV Cable.' Road crossing at this section mandates underbore at 1000mm minimum depth. Working within proximity of live HV underground cable requires: (1) Essential Energy DBYD + live locate, (2) possible Essential Energy-approved spotter on site during excavation/bore, (3) Safe Work NSW excavation near services compliance. No template line for third-party energy attendance. Add provisional sum. Damian to confirm Essential Energy requirements for this section before quoting.

## Job Summary
GND OPTUS FIBRE — JOB SUMMARY
EO NUMBER | STATE | SUBURB | CLUSTER | DELIVERABLE | DESIGN VER | COUNCIL(S) | STATUS
EO35714250 | VIC | Altona North | GK366 South Kingsville | Fibre Lead-in | v0 Preliminary | Hobsons Bay CC | 🔴 3 critical, 3 other gaps
EO36932149 | SA | Golden Grove | TH607 TXM Metro NGCE | Backbone Fibre | v0 Preliminary | City of Salisbury / DIT SA | 🔴 4 critical, 1 other gaps
EO38407216 | SA | North Adelaide | TXM NGCE-Fibre | Backbone Fibre | v0 Preliminary | City of Adelaide / Prospect / DIT SA | 🔴 4 critical, 1 other gaps
EO46092659 | VIC | Tootgarook | GL168 TXM 5G GF FY26 | Fibre Lead-in | v0 Preliminary | Mornington Peninsula SC | 🔴 4 critical, 3 other gaps
EO49466087 | NSW | Thurgoona | GL168 TXM 5G GF FY26 | Fibre Lead-in | v0 Preliminary | Albury City Council | 🔴 5 critical, 2 other gaps

## Variation Risk
GND OPTUS FIBRE — VARIATION RISK TRACKER
Drawing-level anomalies and Hard Stops. Damian to review before submitting any quote.
EO# | SECTION | ANOMALY / RISK | CLASS | GND EXPOSURE | RECOMMENDED ACTION
ALL JOBS | All | Design Version 0 (Preliminary) — all 5 jobs | 🟡 AMBER | Scope change after mobilisation on any job | Confirm scope lock with Optus PE before quoting start date on each job
EO38407216 | 001 | MH congested — duct path unclear | 🔴 HARD STOP | Potholing + delay if duct cannot be proven | Do not fix-price. Provisional sum for duct location works.
EO38407216 | 007 | Outgoing duct deep and dark, unable to see | 🔴 HARD STOP | Potholing + possible re-route | Telstra RRP + site investigation before cable haul.
EO38407216 | 007 | Telstra records conflict with field observation re duct path | 🔴 HARD STOP | Route may change — duct metres at risk | Telstra RRP must clarify duct path before W2.
EO38407216 | 009 | Deep MH on narrow footpath — access constraint | 🟡 AMBER | Extended labour + traffic management | Allow traffic management provisional sum.
EO38407216 | All | EM30 Built Heritage overlay — approval required | 🔴 HARD STOP | Pre-construction delay weeks to months | Engage City of Adelaide Heritage before mobilisation.
EO36932149 | 003/004 | Telstra ACM pits — potential asbestos cement | 🔴 HARD STOP | Hazmat removal + specialist subcontractor | Confirm ACM with Telstra before quoting. Get hazmat quote.
EO46092659 | 001 | Unable to locate pit — seems buried. Contractor to locate & prove ducts | 🔴 HARD STOP | Potholing scope not in BoQ | Add potholing provisional sum. Do not fix-price civil until located.
EO46092659 | 002 | BEP-KCFF: Telstra pit not located — check lead-in route | 🔴 HARD STOP | Route may change; BEP location TBC | Site investigation required before quoting P50 run length.
EO46092659 | 002 | 2× pits unable to locate at time of survey | 🔴 HARD STOP | Multiple potholing events + delay | Provisional sum ×2. Telstra RRP required.
EO46092659 | 002 | Dirt in pit — unable to see duct face, prove ducts prior to works | 🟡 AMBER | Duct proving delay before cable haul | Allow 1 day duct proving per pit. Include in W2 prelims.
EO46092659 | 002 | ODU layout drawing not available — Rack and RU TBC | 🔴 HARD STOP | Internal works scope undefined | Do not price internal works until ODU layout confirmed.
EO46092659 | All | EM21 Aboriginal Heritage Sensitive Area — CHMP may be required | 🔴 HARD STOP | 6-12 month CHMP process if triggered; works cannot proceed without approval | Confirm CHMP status with Optus. Do not mobilise without written approval.
EO49466087 | 001 | Pit not located — possibly bypassed (Thurgoona Dr / Thurgoona Trl) | 🔴 HARD STOP | Route may change if pit is bypassed | Confirm with Telstra before W2. If bypassed, duct continuity must be reconfirmed.
EO49466087 | 002 | 134m from last pit located in field — duct continuity unconfirmed | 🟡 AMBER | Potholing or partial re-route risk over 134m gap | Telstra DBYD + field locate before committing 180m haul section.
EO49466087 | 007 | Pit not located, contractor to confirm (Kerr Rd area) | 🔴 HARD STOP | Potholing + possible re-route | Add provisional sum. Do not fix-price Section 007 civil.
EO49466087 | 009 | Pit not located + NBN-owned pit — different access process | 🔴 HARD STOP | NBN Co field service order required (separate to Telstra RRP); pit location unknown | Damian to confirm NBN Co access process with Optus PM before quoting Section 009. Do not fix-price.
EO49466087 | 008 | Essential Energy Underground HV Cable — bore proximity at Pickworth St road crossing | 🔴 HARD STOP | Legal obligation to comply with Safe Work NSW excavation near live HV; possible Essential Energy spotter required during bore | Confirm Essential Energy requirements before W2 mobilisation on Section 008. Add spotter/attendance allowance as provisional sum.
EO49466087 | 004 | Install pit away from tree drip line — EM35 constraint | 🟡 AMBER | Pit position adjustment required; hand dig if within drip line | Locate trees before setting out pit position. Mark drip line boundary. May affect road/footpath permit alignment.