## Hard Stops (P0)
GND Civil — RC3 Hard Stop Registry (P0) ¦ Cannot proceed without resolution ¦ Feb 2026
A Hard Stop means GND cannot accept commercial responsibility for this element at a fixed price until the named condition is resolved. Hard Stops are NEVER softened in language. 'Cannot proceed without resolution' — not 'may require attention'.
Code | Condition / Trigger | Drawing Signal Language | Why Hard Stop (not provisional sum) | Resolution Action | Resolution Owner | Gate | States Affected | Constitution Ref
HS-001 | Telstra pit: UNLOCATED or BURIED | "cannot be located" / "unable to locate" / "buried under" | GND cannot bore past an unlocated third-party asset. RRP is not a formality — it is the condition that makes the bore legal and safe. | Lodge Telstra RRP immediately. Craig to pothole at pre-mob walk. Do not fix-price civil on affected section until pit is located in writing. | Damian | Pre-mob / W1 | ALL | Constitution Principle 3
HS-002 | ACM (asbestos cement) pit — confirmed or suspected | "ACM" / "asbestos" in pit description or drawing note | Hazmat removal scope, cost, and programme impact cannot be estimated without a licensed hazmat assessment. A price without this is a guess that could be wildly wrong. | Damian to engage licensed hazmat contractor before quoting. Do not include pit work in base quote. Exclude with note. | Damian | Pre-quote | SA, NSW | Constitution Principle 3
HS-003 | EM30 Heritage overlay (SA) | EM30 code in any section of SA drawing | Work cannot legally commence without written Council Heritage approval. No approval = no mobilisation. This is a legal fact, not a risk. | Damian to engage relevant SA council heritage team before mobilisation. Quote cover note: 'Will not mobilise without written heritage approval.' | Damian | Pre-mob | SA | Constitution Principle 3
HS-004 | EM21 Aboriginal Heritage CHMP (VIC) | EM21 code in any section of VIC drawing | CHMP process is 6–12 months. This is a programme reality that must be resolved before GND commits to a start date. Not a delay risk — a fact. | Confirm CHMP status with Optus PM before quoting timeline. Do not commit to start date without CHMP clearance in writing. | Damian / Optus PM | Pre-quote | VIC | Constitution Principle 3
HS-005 | Essential Energy HV cable in bore path | "Essential Energy" near bore path / "live HV" / "high voltage" | Live HV infrastructure requires Essential Energy involvement. GND cannot bore near live HV without their confirmation of clearances and depth requirements. | Damian to engage Essential Energy before W2. Add provisional sum for attendance costs. Do not fix-price bore in affected section. | Damian / Essential Energy | Pre-W2 | NSW, VIC | Constitution Principle 3
HS-006 | NBN Co pit or duct in route path | "NBN" pit or duct in duct path or adjacent to bore | NBN Co access process is materially different from Telstra RRP. GND does not have a confirmed process for NBN Co access. Must be confirmed with Optus PM before quoting. | Damian to confirm NBN Co access process with Optus PM. Exclude affected section until process confirmed. | Damian / Optus PM | Pre-quote | ALL | Constitution Principle 3
HS-007 | Design Version 0 + mobilisation request | Design v0 / 'Preliminary' / 'For Review' in drawing title block | Quoting a fixed price on a preliminary design and mobilising before design confirmation is how scope changes become losses. | Quote can be prepared. Cover note must state: 'GND will not mobilise until scope lock confirmed by Optus PE in writing.' No exceptions. | Karen (cover note) | Pre-mob | ALL | Constitution Principle 3

## Amber Gates (P1)
GND Civil — RC3 Amber Gate Registry (P1) ¦ Proceed only after client instruction or site confirmation ¦ Feb 2026
An Amber Gate means GND can price the item as a provisional sum with a specific trigger, resolution path, and gate wave. Unlike a Hard Stop, the resolution path is known and the cost can be estimated within a reasonable range.
Code | Condition / Trigger | Drawing Signal Language | Provisional Sum Estimate Range | Resolution Action | Resolution Owner | Gate Wave | Invoice Trigger | Notes
AG-001 | Telstra pit: condition unknown or depth unknown | "condition unknown" / "depth unknown" / "records indicate" | $400–$800 per pit | Craig to inspect on pre-mob walk. Pothole if depth uncertain. Confirm condition before W2 bore in affected section. | Craig | W1 | On pit inspection and condition confirmation | Upgrade to HS-001 if pit cannot be located at all
AG-002 | Preliminary design (v0) — scope change risk | "v0" / "Preliminary" / "For Review" in title block | 5–10% of base quote | Note in quote: 'Quoted on v0. GND will submit variation on scope change.' Obtain scope lock from Optus PE before mobilisation. | Karen | Pre-mob | On Optus PE written scope lock confirmation | Upgrade to HS-007 if mobilisation requested before scope lock
AG-003 | HDD bore proximity to existing Optus assets | Bore path within 1m of existing Optus infrastructure | $500–$1,500 per bore | HDD-002: Optus rep attendance required during bore. Confirm with Optus PM before scheduling W2 bore. | Karen / Optus PM | W2 | On Optus PE sign-off of bore completion | Attendance cost charged as variation if Optus rep required
AG-004 | Telstra technician attendance per breakout | Each Telstra breakout in BoQ | $350–$600 per breakout | Book Telstra tech attendance with RRP submission. Confirm booking before W3. | Karen | W3 | On Telstra tech attendance confirmation | Add to W3 invoice on completion
AG-005 | Rock or unexpected ground conditions | "possible rock" / drawing note re soil conditions / geotechnical survey absent | $800–$3,000 per section | Craig to assess on walk. If rock suspected, request geotech confirmation from Optus PE before quoting W2 fixed price. | Craig / Damian | W2 | On ground condition confirmation post-potholing | Requires specific PE instruction before claiming variation
AG-006 | Council reinstatement levy — road or footpath disturbed | Any road bore or footpath trench in council road reserve | $500–$2,000 per permit | Confirm reinstatement standard with council at permit stage. Include levy in provisional sum if not confirmed. | Karen | W0 | On council permit confirmation with levy schedule | Varies significantly by council area — check RC4 for same council jobs
AG-007 | EM35 tree protection — hand dig zone | EM35 code with trees within 3m of route | $200–$600 per tree | Craig to count and photograph all trees within 3m on walk. Productivity drops to 25m/day in hand-dig zone. | Craig | W2 | On section completion with photo evidence of tree protection | Adjust timeline W2 duration — 25m/day not 50m/day in EM35 sections
AG-008 | Depth non-conformance rework (AB-007 evidence failure) | AB-007 capture missed before backfill | Full re-excavation cost of segment | Stop. Do not backfill. Escalate to Damian immediately. Options: re-excavation (certain cost) or submit without evidence (uncertain dispute). Damian decides. | Damian | Any | N/A — this is a cost exposure, not a payment trigger | This is a commercial risk not a compliance nuisance. Re-excavation at GND cost if disputed.

## EM Code Reference
GND Civil — EM Code Reference ¦ Plain English translation for Craig & crew ¦ Feb 2026
Source: Optus Environmental Management Plans. This table is the plain-English translation used in DCAF instructions. When a new EM code appears in a drawing that is not in this list, add it here and flag to Damian for classification.
EM Code | Description (formal) | Plain English for Crew (DCAF language) | Variation Risk? | Classification | Notes
EM21 | Aboriginal Heritage — CHMP required (VIC) | Do not mobilise until Optus PM provides written CHMP clearance. This is a 6–12 month government process. Not negotiable. | YES — Hard Stop | HS-004 | Programme reality, not a risk
EM23 | Sediment and erosion control | Install sediment fencing around ALL disturbed ground and drains BEFORE any ground disturbance. Remove only after reinstatement sign-off. | Minor | In scope | Include in materials manifest — RC2 SED-FENCE
EM24 | Pre-construction photos | Photo entire streetscape BEFORE touching anything. Match photos after reinstatement. Both sets go into as-built. | No | In scope | AB evidence requirement
EM25 | Driveway crossings — no open cut | ALL driveway crossings by HDD bore only. No open cut under any driveway. Photo each intact driveway after bore. | Minor — TM | In scope | Affects bore count in BoQ
EM26 | Turf / nature strip reinstatement | Cut turf in neat squares. Stockpile face-down on plastic. Re-lay after trench closed. Water and compact. Optus PE will inspect match before sign-off. | Minor | In scope | Rate: RC1-SELL REINSTATE $24/m2
EM30 | Built heritage (SA) | Do not mobilise until written Council Heritage approval received. Heritage council = +15–20 day permit lead time. Not a risk — a legal requirement. | YES — Hard Stop | HS-003 | SA only
EM35 | Tree protection | Identify ALL trees within 3m of route before W2. Wrap trunks with hessian before any machinery within 3m. Hand dig within drip line — no excavator. Productivity: 25m/day. | YES — Amber AG-007 | AG-007 | Affects timeline W2 duration
EM36 | Contaminated land management | Stop work immediately if unusual soil colour, odour, or materials found. Call Damian. Do not continue until contamination assessment completed. | YES — Hard Stop (if found) | Escalate to Damian | Rare but serious
EM40 | Fauna and flora protection | Do not disturb vegetation beyond the marked work corridor. If any fauna (including nesting birds) found in work zone, stop and call Damian before proceeding. | Minor — delay risk | Amber — escalate | Rare in urban settings
EM41 | Noise and vibration management | No work before 7am or after 6pm Monday–Saturday. No work Sundays or public holidays unless approved by council. | No | In scope | Standard construction hours — confirm with council permit
EM42 | Traffic management | TM plan must be approved before work commences in any road or shared path zone. Crew cannot start without approved TM in hand. | Minor — TM cost | In scope | TM subcontractor — RC1-SELL TM-PERSON
EM50 | Stormwater protection | No concrete, grout, or spoil enters stormwater drains. Cover all drains before mixing or pumping. Inspect before leaving site. | No | In scope