## Quote History
GND Civil — RC4 Quote History ¦ Win/Loss outcomes + market signal ¦ Karen updates after every Optus response
PURPOSE: RC4 drives the market signal in Phase 2 (Priced Quote) and Phase V (Rate Validation). Minimum 3 comparable jobs required for a market signal to be generated. Karen: update Win/Loss and Winning Bid columns as soon as Optus responds.
Order Number | Date Submitted | Suburb | Council Area | State | Complexity Tier | GND Quoted ($) | Win / Loss | Winning Bid ($) | Variance % | Cluster / Job Type | Key Notes / Lessons
EO35714250 | Feb 2026 | Altona North | Hobsons Bay CC | VIC | Medium | 101836 | PENDING |  |  | GK366 Small Cells | Design v0. Buried pit D + unlocated P9. Hakan (PE). Telstra RRP required before W2.
EO36932149 | Feb 2026 | Golden Grove | City of Salisbury | SA | High |  | NOT QUOTED |  |  | TH607 NGCE Fibre | ACM pit HS-002 — cannot quote until hazmat scope confirmed by Damian.
EO38407216 | Feb 2026 | North Adelaide / Fitzroy | City of Adelaide + City of Prospect | SA | High |  | NOT QUOTED |  |  | TXM NGCE-Fibre O5NA | EM30 heritage all 9 sections HS-003. Do not mobilise without written Council Heritage approval.
EO46092659 | Feb 2026 | Tootgarook | Mornington Peninsula Shire | VIC | High |  | NOT QUOTED |  |  | GL168 5G GF Fibre FY26 | EM21 CHMP HS-004 — 6–12 months. 5 unlocated pits. Do not commit start date.
EO49466087 | Feb 2026 | Thurgoona | Albury City Council | NSW | High |  | NOT QUOTED |  |  | GL168 5G GF Fibre FY26 | NBN Co pit HS-006 + Essential Energy HV HS-005. Both Hard Stops require Damian resolution before quoting.
MARKET SIGNAL SUMMARY ¦ Auto-updates as rows are added
Total jobs logged: | [5 empty] | 5
Jobs with outcome (Win or Loss): | [5 empty] | 0
Win rate (all jobs with outcome): | [5 empty] | -
Avg GND quoted (wins): | [5 empty] | -
Avg winning bid (all outcomes): | [5 empty] | -

## Market Intelligence Feed
GND Civil — Market Intelligence Feed ¦ /listen entries paste here ¦ Feb 2026
Paste /listen output entries here as they are generated. Each entry = one field observation from Damian, Craig, or Karen. This feed is the source for Cache E loading in the Ingestion protocol. Tag-search by suburb, council, PE name, or carrier type.
Date | Source (Damian/Craig/Karen) | Order / Context | Category | Observation | Action Items (⚡) | Tags | Status
Feb 2026 | Damian | EO35714250 | TELSTRA-INFRASTRUCTURE | Telstra Pit D likely buried ~400mm under 2022 footpath reseal. Hobsons Bay CC resurfaced Collins Ave in 2022 after pit was installed. Pit D may not be accessible without council records confirming depth. | ⚡ Damian — call Hobsons Bay council records before Craig's walk to confirm 2022 reseal depth over Pit D location. | #altona-north #hobsons-bay #telstra-buried-pit #EO35714250 | OPEN
Feb 2026 | Damian | EO35714250 | PE-RELATIONSHIP | Hakan (Optus PE, Victoria) expects SWMS submitted before kickoff request — not just on site on day 1. Also checks first aid kit expiry date specifically, not just presence of kit. | ⚡ Karen — add Hakan SWMS-before-kickoff requirement to all VIC DCAF pre-mob checklists. ⚡ Craig — check first aid kit expiry date before every VIC job kickoff. | #hakan-pe #victoria #pe-relationship #EO35714250 | ACTIVE — apply to all VIC jobs
Feb 2026 | Damian | EO36932149 | TELSTRA-INFRASTRUCTURE | Pit G08 confirmed ACM (asbestos cement) in Golden Grove SA job. Hazmat contractor required before any works on or near that pit. Cannot estimate scope without licensed assessment. | ⚡ Damian — engage hazmat contractor for G08 assessment before quoting EO36932149. | #golden-grove #city-of-salisbury #acm-pit #telstra-acm #EO36932149 | BLOCKED — awaiting hazmat assessment
Feb 2026 | Karen | EO38407216 | COUNCIL-AUTHORITY | EO38407216 North Adelaide / Fitzroy spans three council jurisdictions: City of Adelaide, City of Prospect, and Dept for Infrastructure & Transport SA. EM30 heritage applies across all 9 sections. Three separate permit applications may be required. | ⚡ Karen — confirm with Optus PM whether single heritage application covers all three jurisdictions or separate applications needed for each. | #north-adelaide #fitzroy #city-of-adelaide #city-of-prospect #em30-heritage #sa #EO38407216 | OPEN — awaiting Optus PM confirmation

## Usage Guide
RC4 Usage Guide ¦ How this file feeds the quoting system
WHAT RC4 DOES
Market Signal | When the SKILL runs a quote (Phase 2), it reads RC4 Quote History and calculates: avg GND quoted, avg winning bid, and win rate for the same suburb/council/complexity tier. If ≥3 comparable jobs exist, a market signal is generated and the Market Override column is flagged in the priced quote.
Rate Validation | Phase V (/validate command) uses RC4 to flag any line items where GND's rate is >10% above or below comparable jobs. This is the rate calibration loop — it closes the gap between estimated rates and field-validated rates.
Intelligence Feed | The Market Intelligence Feed tab stores all /listen entries. When the Ingestion protocol runs Cache E loading, it searches this tab for suburb, council, PE name, and carrier type matches.
HOW TO MAINTAIN RC4
After every Optus response | Karen updates Quote History: Win/Loss, Winning Bid ($). The Variance % formula calculates automatically.
After every /listen entry | Paste the formatted /listen output into Market Intelligence Feed. One row per observation.
Quarterly review | Damian reviews win rate by suburb and complexity tier. If win rate < 40% in any tier, review subcontractor rates (RC1-COST) or market pricing strategy — not the margin target.
WHAT RC4 IS NOT
Not a financial model | RC4 does not calculate GND's revenue or profit. It tracks market outcomes to calibrate future quotes.
Not a CRM | RC4 does not manage Optus relationships. PE observations live in Market Intelligence Feed — not in a CRM field.
Not a project tracker | RC4 does not track job progress. That is the DCAF system and Konect.